## Gant Chart (planned)
|  |  | August | [9 empty] | September
S/N | Task Description | Assigned To | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5
1 | Game Concept | Team | bar: August 18
2 | Meet Supervisor | Team | bar: August 18 to August 19
3 | Technical Design Document | Kennard | bar: August 19
4 | Project Proposal | Ryan | bar: August 19
5 | Level Design | Team | bar: August 19
6 | Items/Inventory | Wei Xiang | bar: August 19 to August 22
7 | Skills | Kennard | bar: August 19 to August 22
8 | Sprites and Animation | Ryan | bar: August 19 to August 22
9 | Textures | Ryan | bar: August 19 to August 22
10 | Level Transition | Wei Xiang | bar: August 25 to August 27
11 | Enemy AI | Kennard | bar: August 25 to August 28
12 | User Interface Programming | Ryan | bar: August 25 to August 28
13 | Experience System | Wei Xiang | bar: August 28 to September 1
14 | Game Physics | Kennard | bar: August 29 to September 3
15 | Sound | Ryan | bar: August 29 to September 3
16 | Prepare Presentation | Team | bar: September 4
17 | Presentation | Team | bar: September 5

## Gant Chart (Actual)
|  |  | August | [9 empty] | September
S/N | Task Description | Assigned To | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5
3 | Technical Design Document | Kennard | bar: August 19
7 | Skills | Kennard | bar: August 19 to August 22; August 28
11 | Enemy AI | Kennard | bar: August 26 to August 28
14 | Game Physics | Kennard | bar: August 22 to August 26
4 | Project Proposal | Ryan | bar: August 19
8 | Sprites and Animation | Ryan | bar: August 19 to August 26
9 | Textures | Ryan | bar: August 19 to August 20
12 | User Interface Programming | Ryan | bar: August 25; August 27 to August 28
15 | Sound | Ryan | bar: August 25
1 | Game Concept | Team | bar: August 18
2 | Meet Supervisor | Team | bar: August 18 to August 19; August 21
5 | Level Design | Team | bar: August 20
16 | Prepare Presentation | Team
17 | Presentation | Team
6 | Items/Inventory | Wei Xiang | bar: August 19 to August 21
10 | Level Transition | Wei Xiang | bar: August 22 to August 25
13 | Experience System | Wei Xiang | bar: August 26 to August 28

## Task List
Task | Team member | Planned start date | Planned end date
Items & Inventory | Wei Xiang | 2014-08-19 | 2014-08-22
Level Transitions | Wei Xiang | 2014-08-25 | 2014-08-27
Experience System | Wei Xiang | 2014-08-28 | 2014-09-01
Skills | Kennard | 2014-08-19 | 2014-08-22
Enemy AI | Kennard | 2014-08-25 | 2014-08-28
Game Physics | Kennard | 2014-08-29 | 2014-09-03
Sprites & Animation | Ryan | 2014-08-19 | 2014-08-22
User Interface Programming | Ryan | 2014-08-25 | 2014-08-28
Sound | Ryan | 2014-08-29 | 2014-09-03